## Top Page
Installation Check Sheet
Master's Signature:
Date:
Dockyard:
Hull No.:
Vessel Name:
Technician:

## Conning Display
Equipment : Conning Display
No.1 | Type： |  |  | Serial No.:
No.2 | Type： |  |  | Serial No.:
Tick in the result column, if the result is proper.
Installation Check |  |  |  |  | Conning No.
Check Item | Confirmation | Confirmation | Confirmation | Confirmation | 1 | 2
1. Display unit (main unit)
| Maintenance space is adequate. | Maintenance space is adequate. | Maintenance space is adequate. | Maintenance space is adequate.
Fitting bolt | All bolts for fitting the display unit are fastened properly. | All bolts for fitting the display unit are fastened properly. | All bolts for fitting the display unit are fastened properly. | All bolts for fitting the display unit are fastened properly.
| No damage to knobs etc. on the operation panel. | No damage to knobs etc. on the operation panel. | No damage to knobs etc. on the operation panel. | No damage to knobs etc. on the operation panel.
Earth | Ground earth is connected properly by copper strap.
Connection | Each wire is tightened to the correct terminal respectively.
Function Check |  |  |  |  | Conning No.
Check Item | Confirmation |  |  |  | 1 | 2
1. Checking input data | Check that input data can be read correctly.
| (If there is equipment being connected, put a x mark in the square) |  | □ | ・GYRO (step sig or NMEA)
|  |  | □ | ・LOG ( 200P/NM or NMEA )
|  |  | □ | ・GPS
|  |  | □ | ・AIS
|  |  | □ | ・ARPA ( No1RADER , No2RADAR )
|  |  | □ | ・RADAR Echo ( No1RADER , No2RADAR )
|  |  | □ | ・RUDDER ANGLE ( SYNCHRO or NMEA )
|  |  | □ | ・WIND DIRECTION ( SYNCHRO or NMEA )
|  |  | □ | ・WIND SPEED ( ANALOG or NMEA )
|  |  | □ | ・M/E RPM （ Analog signal or NMEA )
|  |  | □ | ・NAVTEX
|  |  | □ | ・DOPPLER SONAR ( NMEA and 200P/NM )
|  |  | □ | ・NAV WORK STATION
|  |  | □ | ・Others ( )
|  |  | □ | ・Others ( )
|  |  | □ | ・Others ( )
2. Checking output data | Check that output data is output correctly.
| (If there is equipment being connected, put a x mark in the square) |  | □ | ・AUTO PILOT
|  |  | □ | ・Conning Display
|  |  | □ | ・VDR
|  |  | □ | ・CONTACT ALARM SIG （OFF ROUTE)
|  |  | □ | ・CONTACT ALARM SIG （WAYPOINT APPROACH)
|  |  | □ | ・CONTACT ALARM SIG （HEADING ERROR)
|  |  | □ | ・CONTACT ALARM SIG （ECDIS FAIL)
|  |  | □ | ・CONTACT ALARM SIG （VIGILANCE)
|  |  | □ | ・CONTACT ALARM SIG （POSITION)
|  |  | □ | ・CONTACT ALARM SIG （ROUTE ALARM)
|  |  | □ | ・CONTACT ALARM SIG （A/P ALARM ANTS)
3. Checking chart display | Check that the chart can be installed and displayed.
|  |  | □ | C-MAP Ver2
|  |  | □ | C-MAP Ver3
|  |  | □ | ENC
|  |  | □ | ARCS
Erase any sample map before the delivery.
4. Checking track data | Check that the system is able to store and display the past track after power cycle (power off On).
5. Checking UPS operation | Use the distribution board to turn off input power and turn it on again after 10 seconds, and check that the screen is displayed.
6. Checking during sea trial. | Check that each input/output data is displayed correctly.
Installation Company: |  |  |  | Vessel's Name:
Installed by: |  |  |  | Approved by:

## ECDIS
Equipment : ECDIS
No.1 | Type： |  |  | Serial No.:
No.2 | Type： |  |  | Serial No.:
Tick in the result column, if the result is proper.
Installation Check |  |  |  |  | ECDIS No.
Check Item | Confirmation | Confirmation | Confirmation | Confirmation | 1 | 2
1. Display unit (main unit)
| Maintenance space is adequate. | Maintenance space is adequate. | Maintenance space is adequate. | Maintenance space is adequate.
Fitting bolt | All bolts for fitting the display unit are fastened properly. | All bolts for fitting the display unit are fastened properly. | All bolts for fitting the display unit are fastened properly. | All bolts for fitting the display unit are fastened properly.
| No damage to knobs etc. on the operation panel. | No damage to knobs etc. on the operation panel. | No damage to knobs etc. on the operation panel. | No damage to knobs etc. on the operation panel.
Earth | Ground earth is connected properly by copper strap.
Connection | Each wire is tightened to the correct terminal respectively.
Function Check |  |  |  |  | ECDIS No.
Check Item | Confirmation |  |  |  | 1 | 2
1. Checking input data | Check that input data can be read correctly.
| (If there is equipment being connected, put a x mark in the square) |  | □ | ・GYRO (step sig or NMEA)
|  |  | □ | ・LOG ( 200P/NM or NMEA )
|  |  | □ | ・GPS
|  |  | □ | ・AIS
|  |  | □ | ・ARPA ( No1RADER , No2RADAR )
|  |  | □ | ・RADAR Echo ( No1RADER , No2RADAR )
|  |  | □ | ・RUDDER ANGLE ( SYNCHRO or NMEA )
|  |  | □ | ・WIND DIRECTION ( SYNCHRO or NMEA )
|  |  | □ | ・WIND SPEED ( ANALOG or NMEA )
|  |  | □ | ・M/E RPM （ Analog signal or NMEA )
|  |  | □ | ・NAVTEX
|  |  | □ | ・DOPPLER SONAR ( NMEA and 200P/NM )
|  |  | □ | ・NAV WORK STATION
|  |  | □ | ・NETWORK
|  |  | □ | ・Others ( )
|  |  | □ | ・Others ( )
2. Checking output data | Check that output data is output correctly.
| (If there is equipment being connected, put a x mark in the square) |  | □ | ・AUTO PILOT
|  |  | □ | ・Conning Display
|  |  | □ | ・VDR
|  |  | □ | ・CONTACT ALARM SIG （OFF ROUTE)
|  |  | □ | ・CONTACT ALARM SIG （WAYPOINT APPROACH)
|  |  | □ | ・CONTACT ALARM SIG （HEADING ERROR)
|  |  | □ | ・CONTACT ALARM SIG （ECDIS FAIL)
|  |  | □ | ・CONTACT ALARM SIG （VIGILANCE)
|  |  | □ | ・CONTACT ALARM SIG （POSITION)
|  |  | □ | ・CONTACT ALARM SIG （ROUTE ALARM)
|  |  | □ | ・CONTACT ALARM SIG （A/P ALARM ANTS)
3. Checking chart display | Check that the chart can be installed and displayed.
|  |  | □ | C-MAP Ver2
|  |  | □ | C-MAP Ver3
|  |  | □ | ENC
|  |  | □ | ARCS
Erase any sample map before the delivery.
4. Checking track data | Check that the system is able to store and display the past track after power cycle (power off On).
5. Checking UPS operation | Use the distribution board to turn off input power and turn it on again after 10 seconds, and check that the screen is displayed.
6. Checking during sea trial. | Check that each input/output data is stably displayed.
Check that automatic navigation can be performed normally (if connection with "Auto pilot" is available).
Installation Company: |  |  |  | Vessel's Name:
Installed by: |  |  |  | Approved by:

## Doppler SONAR_Log
Equipment : Doppler SONAR / Log 1/2
| Type： |  | Serial No.:
Tick in the result column, if the result is proper.
Installation Check
Check Item | Confirmation |  |  |  | Result
1. Main Display unit
Fitting bolt | All fitting bolts are fastened properly.
2. Sub Display unit
Fitting bolt | All fitting bolts are fastened properly.
3. Wing Display unit
Fitting bolt | All fitting bolts are fastened properly.
waterproof | Cable glands are fastened and waterproofed properly.
4. Signal Distributor
Fitting bolt | All fitting bolts are fastened properly. | All fitting bolts are fastened properly. | All fitting bolts are fastened properly. | All fitting bolts are fastened properly.
| Unit is not misformed or twisted due to uneven mounting surface. | No inclination and distortion after installed and fastened. | No inclination and distortion after installed and fastened. | No inclination and distortion after installed and fastened.
Ground earth is connected properly by copper strap.
5. Signal processor
Fitting bolt | All fitting bolts are fastened properly. | All fitting bolts are fastened properly. | All fitting bolts are fastened properly. | All fitting bolts are fastened properly.
| Unit is not misformed or twisted due to uneven mounting surface. | No inclination and distortion after installed and fastened. | No inclination and distortion after installed and fastened. | No inclination and distortion after installed and fastened.
| Transducer cable is cut to appropriate length. | Residue of cables for transducer are cut. | Residue of cables for transducer are cut. | Residue of cables for transducer are cut.
Ground earth is connected properly by copper strap!.
| Transducer cable and signal cables for signal processor are installed separately. | Cables for transducer and cables for signal processor are installed separately. | Cables for transducer and cables for signal processor are installed separately. | Cables for transducer and cables for signal processor are installed separately.
6. Transducer（outside surface) | No possibility for air bubble to accumulate around transducer.
| Evenness of transducer surface is within the tolerance to the outside surface of bottom plate. | Evenness of transducer surface is within the tolerance to the outside surface of bottom plate. | Evenness of transducer surface is within the tolerance to the outside surface of bottom plate. | Evenness of transducer surface is within the tolerance to the outside surface of bottom plate.
| No visible damage and surface is clean (no paint or other foreign material) | No damaged part. | No damaged part. | No damaged part.
Function Check
to next page
Equipment : Doppler SONAR / Log 2/2
Tick in the result column, if the result is proper.
Function Check
Check Item | Confirmation |  |  |  | Result
1.Main Display
1.1 Checking display | Check that measured speed data is displayed.
| JLN-550 | □ | ・Main Display （NWW-60 DB or DA、TB、TA ）
| JLN-205 | □ | ・Main Display （NWW-65）
2.Remote Display
2.1 Checking display | Check that measured speed data is displayed.
| (If there is equipment being connected, put a x mark in the square) | □ | ・Wing Display （NWW-61D or T ）
|  | □ | ・Secondary indicator (NWW-49 ship speed and distance)
|  | □ | ・Secondary indicator (NWW-5 longitudinal ship speed)
|  | □ | ・Secondary indicator (NWW-7 electromagnetic counter)
|  | □ | ・Secondary indicator (NWW-16 longitudinal ship speed and distance meter)
|  | □ | ・Analog indicator (NWW-24 flash mount)
|  | □ | ・Analog indicator (NWW-25 waterproof type)
|  | □ | ・Analog indicator (NWW-26 panel mount)
| JLN-205 | □ | ・Secondary indicator（NWW-65S）
3.Signal Distributor
3.2 Checking input data | Check that input data can be received normally.
|  | □ | ・GPS （NMEA）
| JLN-550 | □ | ・GYRO （NMEA）
| JLN-550 | □ | ・ROT （NMEA）
3.3 Checking output data | Check that data is output to each piece of equipment normally.
| (If there is equipment being connected, put a x mark in the square) | □ | ・NO. 1 RADAR ( NMEA or 200P/NM )
|  | □ | ・NO. 2 RADAR ( NMEA or 200P/NM )
|  | □ | ・GYRO ( NMEA or 200P/NM )
|  | □ | ・AUTO PILOT ( NMEA or 201P/NM )
|  | □ | ・Data logger ( NMEA or 200P/NM )
|  | □ | ・ECDIS ( NMEA or 200P/NM )
|  | □ | ・Conning Disp ( NMEA or 200P/NM )
|  | □ | ・Others ( NMEA or 200P/NM ）
4.Signal Processor
4.1 Checking transmission operation | Check that the transmission LED on the signal processor blinks.
CMB-319 240k transmission block CD244 TX-LED (JLN-550)
JLN-550 | CMN-633 2M transmission block CD417, CD419 TX-LED (JLN-550)
5.Total
5.1 Checking interference | Check that there is no interference from other sounder.
5.2 Calibration | Check that actual ship speed error is calibrated.
5.3 Running test | Check that bubbles do not affect the sonar.
Installation Company: |  |  | Vessel's Name:
Installed by: |  |  | Approved by:

## Echo Sounder
Equipment : Echo sounder
No.1 | Type： | Serial No.:
No.2 | Type： | Serial No.:
E/S No.
|  |  | 1 | 2
Install position (BOW / STERN)
|  | Frequency (50kHz / 200kHz) | kHz | kHz
Tick in the result column, if the result is proper.
Installation Check |  |  | E/S No.
Check Item | Confirmation |  | 1 | 2
1. Recorder(Display)
Fitting bolt | All fitting bolts are fastened properly. | All fitting bolts are fastened properly.
| Unit is not misformed or twisted due to uneven mounting surface. | No inclination and distortion after installed and fastened.
2. Matching box (Connection Box)
Fitting bolt | All fitting bolts are fastened properly. | All fitting bolts are fastened properly.
Cable Gland | Cable glands are fastened and waterproofed properly. | Cable glands are fastened and waterproofed properly.
3. Transducer
Transducer（outside surface) | Evenness of transducer surface is within the tolerance to the outside surface of bottom plate. | Evenness of transducer surface is within the tolerance to the outside surface of bottom plate.
| No visible damage and surface is clean (no paint or other foreign material) | No damaged part.
Function Check |  |  | E/S No.
Check Item | Confirmation |  | 1 | 2
1. Recorder(Display)
1.1 Transmission block | Check that the transmission monitor LED lights.
1.2 Reception block | Check that the sensitivity and STC control operate normally.
1.3 Checking record | Check that the sea bed (bottom) echo is recorded (or displayed).
1.4 Interference | Check that there is no interference from other acoustic equipment (doppler sonar, fishfinder and tide meter etc.).
1.5 Water depth measurement | Check that there is no difference between the displayed digital value and the measured depth on the record sheet/display.
1.6 Checking NAV signal input (during NAV data connection only) | Check that own ship position data from the navigation system is recorded (or displayed).
1.7 Checking data output | Check that NMEA data is output normally (ECDIS or Conning Display).
Installation Company: |  | Vessel's Name:
Installed by: |  | Approved by:

## RADAR
Equipment : RADAR 1/2
No.1 | Type： |  |  | Serial No.:
No.2 | Type： |  |  | Serial No.:
No.3 | Type： |  |  | Serial No.:
Tick in the result column, if the result is proper.
Installation Check | [6 empty] | RADAR No.
Check Item | Confirmation |  |  |  | 1 | 2 | 3
1. Antenna scanner | When the antenna turns, there is no abnormal noise.
Install position of X-BAND and S-BAND are correct.
The scanner motor voltage and the power supply voltage are correct (same).
| Maintenance space is adequate. | Maintenance space is adequate. | Maintenance space is adequate. | Maintenance space is adequate.
Keep maintenance space to open both sides of the scanner cover.
Fitting bolt | Bolts for fitting antenna scanner are fastened properly.
Earth | silicone rubber is applied to the bolts for fitting copper earth plate | silicone rubber is pasted to the bolts for fitting copper earth plate | silicone rubber is pasted to the bolts for fitting copper earth plate | silicone rubber is pasted to the bolts for fitting copper earth plate
| Bolts for fastening antenna cover are fastened properly. | Bolts for fastening antenna cover are fastened properly. | Bolts for fastening antenna cover are fastened properly. | Bolts for fastening antenna cover are fastened properly.
Waveguide, Coaxial cable | Flexible wave guide and coaxial cable are jointed properly. | Flexible wave guide and coaxial cable are jointed properly. | Flexible wave guide and coaxial cable are jointed properly. | Flexible wave guide and coaxial cable are jointed properly.
| Flexible wave guide and coaxial cable are supported properly. | Flexible wave guide and coaxial cable are supported properly. | Flexible wave guide and coaxial cable are supported properly. | Flexible wave guide and coaxial cable are supported properly.
| Flexible wave guide and coaxial cable (scanner side) are protected from vibration. | Flexible wave guide and coaxial cable are supported properly. | Flexible wave guide and coaxial cable are supported properly. | Flexible wave guide and coaxial cable are supported properly.
Flexible wave guide and coaxial cable are not bent more than specified.
Deck penetrations for the waveguide or coaxial cable are sealed sufficiently with putty or the like.
2. Display
Fitting bolt | All fitting bolts are fastened properly. | All fitting bolts are fastened properly. | All fitting bolts are fastened properly. | All fitting bolts are fastened properly.
No damage to the knobs etc. on the operation panel.
3. Transceiver
Fitting bolt | Unit is not misformed or twisted due to uneven mounting surface. | No inclination and distortion of transceiver after installed and fastened. | No inclination and distortion of transceiver after installed and fastened. | No inclination and distortion of transceiver after installed and fastened.
Inclination, Distortion | Transmitter is fitted sqaure and not tilted at an angle or askew. | 送受信機の傾き、締め付けによる筐体のゆがみがない事。 | 送受信機の傾き、締め付けによる筐体のゆがみがない事。 | 送受信機の傾き、締め付けによる筐体のゆがみがない事。
| Earth wiring is proper. | Earth wiring is proper. | Earth wiring is proper. | Earth wiring is proper.
| Flexible wave guide and coaxial cable are jointed properly. | Flexible wave guide and coaxial cable are jointed properly. | Flexible wave guide and coaxial cable are jointed properly. | Flexible wave guide and coaxial cable are jointed properly.
Function Check
to next page
Equipment : RADAR 2/2
Tick in the result column, if the result is proper.
Function Check | [6 empty] | RADAR No.
Check Item | Confirmation |  |  |  | 1 | 2 | 3
1.Initial setting
Tuning | Check that after tuning adjustment, manual tuning and automatic tuning operate normally.
Direction adjustment | Check that the bearing adjustment has been completed.
Distance adjustment | Check that zero-mile (range) adjustment has been completed.
Checking inter-switch | Check that inter-switch adjustment has been completed (when inter-switch is installed)
2.Checking image.
Sensitivity | Check that radar echo appears during transmission.
Performance monitor | Check that performance monitor adjustment has been completed and the result is recorded on the indicator label .
EBL,VRM | Check that VRM marker and EBL marker appear on the screen and can be adjusted smoothly.
Cursor | Check that cursor works normally.
Characters | Check that character and symbol display normaly.
3. Checking data input | Check that input data can be read and displayed normally.
| (If there is equipment being connected, put a x mark in the square) |  | □ | GYRO (step sig or NMEA)
|  |  | □ | LOG ( 200P/NM or NMEA )
|  |  | □ | GPS
|  |  | □ | AIS
|  |  | □ | DOPPLER SONAR ( NMEA and 200P/NM )
|  |  | □ | ECHO SOUNDER
4. Checking data output | Check that output data is output normally.
| (If there is equipment being connected, put a x mark in the square) |  | □ | ・ARPA DATA （ ECDIS ）
|  |  | □ | ・ALARM DATA （ Conning Display ）
|  |  | □ | ・RGB VIDEO SIGNAL （ VDR ）
|  |  | □ | ・RADAR ECHO SIGNAL （ ECDIS )
|  |  | □ | ・CONTACT ARPA ALARM （Conning Disp or ALA SYS)
|  |  | □ | ・CONTACT SYS ALARM（Conning Disp or ALARM SYS)
5. Checking false echo. | Check false echo. (it should not hinder operation).
Explain any false echo to the crew.
6 Checking ARPA | Check that a target can be manually and automatically acquired, tracked and canceled.
Check that an alarm is generated when a symbol changes to a dangerous ship.
Installation Company: |  |  |  | Vessel's Name:
Installed by: |  |  |  | Approved by:

## GPS receiver
Equipment : GPS receiver
No.1 | Type： |  |  | Serial No.:
No.2 | Type： |  |  | Serial No.:
No.3 | Type： |  |  | Serial No.:
Tick in the result column, if the result is proper.
Installation Check | [6 empty] | GPS No.
Check Item | Confirmation |  |  |  |  | 1 | 2 | 3
1. Antenna(receiver)
No obstacles for the reception around the antenna.
| Maintenance space is adequate. | Maintenance space is adequate. | Maintenance space is adequate. | Maintenance space is adequate. | Maintenance space is adequate.
Fitting base | Antenna (receiver) is mounted/fastened properly. | Screws mounting for fitting antenna (receiver) are fastened properly. | Screws mounting for fitting antenna (receiver) are fastened properly. | Screws mounting for fitting antenna (receiver) are fastened properly. | Screws mounting for fitting antenna (receiver) are fastened properly.
Fitting band | All bands for fitting antenna (receiver) are fastened properly. | All bands for fitting antenna (receiver) are fastened properly. | All bands for fitting antenna (receiver) are fastened properly. | All bands for fitting antenna (receiver) are fastened properly. | All bands for fitting antenna (receiver) are fastened properly.
Junction box | All fitting bolts are fastened properly. | All fitting bolts are fastened properly. | All fitting bolts are fastened properly. | All fitting bolts are fastened properly. | All fitting bolts are fastened properly.
| Connection is done correctly. | Connection is done correctly. | Connection is done correctly. | Connection is done correctly. | Connection is done correctly.
| Screws for fitting front cover are fastened properly. | Screws for fitting front cover are fastened properly. | Screws for fitting front cover are fastened properly. | Screws for fitting front cover are fastened properly. | Screws for fitting front cover are fastened properly.
| Cable gland(s) is fastened properly and silicone rubber is applied. | Cable gland(s) is fastened properly and it is pasted with silicone rubber. | Cable gland(s) is fastened properly and it is pasted with silicone rubber. | Cable gland(s) is fastened properly and it is pasted with silicone rubber. | Cable gland(s) is fastened properly and it is pasted with silicone rubber.
2. Display
| Installation plate is fitted properly. | Installation plate is fitted properly. | Installation plate is fitted properly. | Installation plate is fitted properly. | Installation plate is fitted properly.
Earth | Earth wiring is proper. | Earth wring is proper. | Earth wring is proper. | Earth wring is proper. | Earth wring is proper.
Connector | Rear connectors are fastened to the display unit correctly. | Rear connectors are jointed to the display unit correctly. | Rear connectors are jointed to the display unit correctly. | Rear connectors are jointed to the display unit correctly. | Rear connectors are jointed to the display unit correctly.
Function Check | [6 empty] | GPS No.
Check Item | Confirmation |  |  |  |  | 1 | 2 | 3
1. Checking display unit | Check that there is no abnormality in the LCD panel.
2. Operator panel state | Check that all keys function normally.
3. Satellite reception state | Check that the satellite is received and two-dimensional positioning is acquired several minutes after power-on.
Geodetic data correction is WGS-84.
4. Checking data output | Check that external output data is transferred to the destination normally.
| (If there is equipment being connected, put a x mark in the square) |  | □ | ・Printer
|  |  | □ | ・Radar
|  |  | □ | ・MF/HF
|  |  | □ | ・INM-B/F/C
|  |  | □ | ・ECDIS
|  |  | □ | ・Color Protter
|  |  | □ | ・Echo Sounder
|  |  | □ | ・AIS
|  |  | □ | ・VDR
|  |  | □ | ・Other
2.3 Presence of optional equipment | Buffer unit (NQA-602DC/NQA-4251) Other ( )
3. EMI | Check that the receiver is not subject to interference from radio transmitter and does not cause interference with other equipment during operation.
Installation Company: |  |  |  | Vessel's Name:
Installed by: |  |  |  | Approved by:

## AIS
Equipment : AIS
Type： | Serial No.:
Installation Check |  |  |  |  | Tick in the result column, if the result is proper.
Check Item | Confirmation |  |  |  | Result
1. Transponder
| Maintenance space is adequate | Maintenance space is adequate | Maintenance space is adequate | Maintenance space is adequate
Stainless band for fitting | Transponder is mounted with stainless band. | Transponder is fittied with stainless band. | Transponder is fittied with stainless band. | Transponder is fittied with stainless band.
Earth | Fitting bolt for copper earth plate has silicone rubber applied. | Fitting bolt for copper earth plate is pasted on with silicone rubber. | Fitting bolt for copper earth plate is pasted on with silicone rubber. | Fitting bolt for copper earth plate is pasted on with silicone rubber.
| Signal cable is not fastened too loosely and no vibration happens to the signal cable while ship is vibrating. | Signal cable is not fastened too loosely and no vibration happens to the signal cable while ship is vibrating. | Signal cable is not fastened too loosely and no vibration happens to the signal cable while ship is vibrating. | Signal cable is not fastened too loosely and no vibration happens to the signal cable while ship is vibrating.
Cable for signals | The connector to the transponder is watertproofed properly. | The connector to the transponder is watertproofed properly. | The connector to the transponder is watertproofed properly. | The connector to the transponder is watertproofed properly.
| Cables between the junction boxes are fastened properly. | Cables between the junction boxes are fastened properly. | Cables between the junction boxes are fastened properly. | Cables between the junction boxes are fastened properly.
| Transponder : not scratched, and clean | Transponder : not scratched, and clean | Transponder : not scratched, and clean | Transponder : not scratched, and clean
2. Display
Fitting bolts | All bolts for fitting the display are fastened properly. | All bolts for fitting the display are fastened properly. | All bolts for fitting the display are fastened properly. | All bolts for fitting the display are fastened properly.
| Rear signal cables are fastened properly. | Rear signal caｂles are fastened properly. | Rear signal caｂles are fastened properly. | Rear signal caｂles are fastened properly.
| No damage to the knobs etc. on the display | No damage to the knobs etc. on the display | No damage to the knobs etc. on the display | No damage to the knobs etc. on the display
3. Junction box
Fitting bolt | All bolts for fitting the junction box are fastened properly. | All bolts for fitting the junction box are fastened properly. | All bolts for fitting the junction box are fastened properly. | All bolts for fitting the junction box are fastened properly.
Inclination and Distortion | Unit is not misformed or twisted due to uneven mounting surface. | No inclination and no distortion of J.box. | No inclination and no distortion of J.box. | No inclination and no distortion of J.box.
| Earth is fitted properly as instructed. | Earth is fitted properly as instructed. | Earth is fitted properly as instructed. | Earth is fitted properly as instructed.
| Signal cables and power cables are fastened properly | Signal cables and power cables are fastened properly | Signal cables and power cables are fastened properly | Signal cables and power cables are fastened properly
| Armored cables are fastened properly with cable clamp. | Armored cables are fastened properly with cable cramp. | Armored cables are fastened properly with cable cramp. | Armored cables are fastened properly with cable cramp.
| MMSI | :
| IMO No． | :
Function Check | CALL SIGN | :
Check Item | Confirmation |  |  |  | Result
1. Maintenance
Check that maintenance space is secure.
2. Checking initial setting | Check static data.
|  |  | □ | The ship name, MMSI, IMO No., and call sign are correct.
|  |  | □ | The location and type of position sensor are correct.
|  |  | □ | The location of AIS antenna is correct.
3. Checking operating state
3.1 Checking input data | Check that input data can be read correctly.
| (If there is equipment being connected, put a x mark in the square) |  | □ | • GYRO ( NSK UNIT or NMEA )
|  |  | □ | • POSITION SENSOR (GPS)
|  |  | □ | • DOPPLER SONAR ( NMEA )
|  |  | □ | • ROT
3.2 Checking output data | Check that data is output correctly.
| (If there is equipment being connected, put a x mark in the square) |  | □ | • PILOT PLUG
|  |  | □ | • RADAR （ No.1 • No.2 ）
|  |  | □ | • ECDIS
|  |  | □ | • VDR/S-VDR
|  |  | □ | • ALARM1 CONTACT ALARM SIG
|  |  | □ | • ALARM2 CONTACT ALARM SIG
3.3 Checking self-test function | Execute self-test to check that OK is displayed.
3.4 Checking receive data | Check that information about other ship is displayed.
3.5 Checking transmit data | Check that transmission output is output as the specified value.
3.6 Emergency power operation | Check that the system runs on emergency power.
Installation Company: |  |  |  | Vessel's Name:
Installed by: |  |  |  | Approved by:

## Tow-Way VHF
Equipment : Tow-Way VHF | 1 /
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper. | Result
Check Item | Confirmation | Confirmation | 1
1. Appearance check
1.1 Prime battery | Seal for the primary battery is intact and not tampered with as required. | Seal for the primary battery is left fitted as required.
1.2 Case and strap | No damage to the case and strap, and they are clean. | No damage to the case and strap, and they are clean.
1.3 Fitting of antenna | Antenna is fitted to the equipment properly without looseness. | Antenna is fitted to the equipment properly without looseness
1.4 Operation and indicator panel | Lamps light, and switch and volume work properly. | Lamps light, and switch and volume work properly.
2. Function check
2.1 Receiving | Noise from the speaker can be heard. | Noise from the speaker can be heard.
2.2 Squelch | When the squelch is turned down, noise can be heard. When the squelch is turned up, noise is wiped out. | When the squelch is turned down, noise can be heard. When the squelch is turned up, noise is wiped out.
2.3 Communication | Communicate with another bidirectional radio voice communication equipment and confirm that communication can be achieved properly on both sides. | Communicate with another bidirectional radio voice communication equipment and confirm that communication can be achieved properly on both sides.
3. Battery Charger | Confirm that battery charger charges the bidirectional radio voice communication equipment and lamp of charger changes.
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper. | Result
Check Item | Confirmation | Confirmation | 2
1. Appearance check
1.1 Prime battery | Seal for the primary battery is intact and not tampered with as required. | Seal for the primary battery is left fitted as required.
1.2 Case and strap | No damage to the case and strap, and they are clean. | No damage to the case and strap, and they are clean.
1.3 Fitting of antenna | Antenna is fitted to the equipment properly without looseness. | Antenna is fitted to the equipment properly without looseness
1.4 Operation and indicator panel | Lamps light, and switch and volume work properly. | Lamps light, and switch and volume work properly.
2. Function check
2.1 Receiving | Noise from the speaker can be heard. | Noise from the speaker can be heard.
2.2 Squelch | When the squelch is turned down, noise can be heard. When the squelch is turned up, noise is wiped out. | When the squelch is turned down, noise can be heard. When the squelch is turned up, noise is wiped out.
2.3 Communication | Communicate with another bidirectional radio voice communication equipment and confirm that communication can be achieved properly on both sides. | Communicate with another bidirectional radio voice communication equipment and confirm that communication can be achieved properly on both sides.
3. Battery Charger | Confirm that battery charger charges the bidirectional radio voice communication equipment and lamp of charger changes.
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper. | Result
Check Item | Confirmation | Confirmation | 3
1. Appearance check
1.1 Prime battery | Seal for the primary battery is intact and not tampered with as required. | Seal for the primary battery is left fitted as required.
1.2 Case and strap | No damage to the case and strap, and they are clean. | No damage to the case and strap, and they are clean.
1.3 Fitting of antenna | Antenna is fitted to the equipment properly without looseness. | Antenna is fitted to the equipment properly without looseness
1.4 Operation and indicator panel | Lamps light, and switch and volume work properly. | Lamps light, and switch and volume work properly.
2. Function check
2.1 Receiving | Noise from the speaker can be heard. | Noise from the speaker can be heard.
2.2 Squelch | When the squelch is turned down, noise can be heard. When the squelch is turned up, noise is wiped out. | When the squelch is turned down, noise can be heard. When the squelch is turned up, noise is wiped out.
2.3 Communication | Communicate with another bidirectional radio voice communication equipment and confirm that communication can be achieved properly on both sides. | Communicate with another bidirectional radio voice communication equipment and confirm that communication can be achieved properly on both sides.
3. Battery Charger | Confirm that battery charger charges the bidirectional radio voice communication equipment and lamp of charger changes.
Installation Company: |  | Vessel's Name:
Installed by: |  | Approved by:
Equipment : Tow-Way VHF | 2 /
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper. | Result
Check Item | Confirmation | Confirmation | 4
1. Appearance check
1.1 Prime battery | Seal for the primary battery is intact and not tampered with as required. | Seal for the primary battery is left fitted as required.
1.2 Case and strap | No damage to the case and strap, and they are clean. | No damage to the case and strap, and they are clean.
1.3 Fitting of antenna | Antenna is fitted to the equipment properly without looseness. | Antenna is fitted to the equipment properly without looseness
1.4 Operation and indicator panel | Lamps light, and switch and volume work properly. | Lamps light, and switch and volume work properly.
2. Function check
2.1 Receiving | Noise from the speaker can be heard. | Noise from the speaker can be heard.
2.2 Squelch | When the squelch is turned down, noise can be heard. When the squelch is turned up, noise is wiped out. | When the squelch is turned down, noise can be heard. When the squelch is turned up, noise is wiped out.
2.3 Communication | Communicate with another bidirectional radio voice communication equipment and confirm that communication can be achieved properly on both sides. | Communicate with another bidirectional radio voice communication equipment and confirm that communication can be achieved properly on both sides.
3. Battery Charger | Confirm that battery charger charges the bidirectional radio voice communication equipment and lamp of charger changes.
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper. | Result
Check Item | Confirmation | Confirmation | 5
1. Appearance check
1.1 Prime battery | Seal for the primary battery is intact and not tampered with as required. | Seal for the primary battery is left fitted as required.
1.2 Case and strap | No damage to the case and strap, and they are clean. | No damage to the case and strap, and they are clean.
1.3 Fitting of antenna | Antenna is fitted to the equipment properly without looseness. | Antenna is fitted to the equipment properly without looseness
1.4 Operation and indicator panel | Lamps light, and switch and volume work properly. | Lamps light, and switch and volume work properly.
2. Function check
2.1 Receiving | Noise from the speaker can be heard. | Noise from the speaker can be heard.
2.2 Squelch | When the squelch is turned down, noise can be heard. When the squelch is turned up, noise is wiped out. | When the squelch is turned down, noise can be heard. When the squelch is turned up, noise is wiped out.
2.3 Communication | Communicate with another bidirectional radio voice communication equipment and confirm that communication can be achieved properly on both sides. | Communicate with another bidirectional radio voice communication equipment and confirm that communication can be achieved properly on both sides.
3. Battery Charger | Confirm that battery charger charges the bidirectional radio voice communication equipment and lamp of charger changes.
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper. | Result
Check Item | Confirmation | Confirmation | 6
1. Appearance check
1.1 Prime battery | Seal for the primary battery is intact and not tampered with as required. | Seal for the primary battery is left fitted as required.
1.2 Case and strap | No damage to the case and strap, and they are clean. | No damage to the case and strap, and they are clean.
1.3 Fitting of antenna | Antenna is fitted to the equipment properly without looseness. | Antenna is fitted to the equipment properly without looseness
1.4 Operation and indicator panel | Lamps light, and switch and volume work properly. | Lamps light, and switch and volume work properly.
2. Function check
2.1 Receiving | Noise from the speaker can be heard. | Noise from the speaker can be heard.
2.2 Squelch | When the squelch is turned down, noise can be heard. When the squelch is turned up, noise is wiped out. | When the squelch is turned down, noise can be heard. When the squelch is turned up, noise is wiped out.
2.3 Communication | Communicate with another bidirectional radio voice communication equipment and confirm that communication can be achieved properly on both sides. | Communicate with another bidirectional radio voice communication equipment and confirm that communication can be achieved properly on both sides.
3. Battery Charger | Confirm that battery charger charges the bidirectional radio voice communication equipment and lamp of charger changes.
Installation Company: |  | Vessel's Name:
Installed by: |  | Approved by:

## SART
Equipment : SART
Type： | Serial No.:
Installation and function Check/Test |  |  | Tick in the result column, if the result is proper.
Check Item | Confirmation |  | Result
1. Installation | SART can be taken off easily from the stow position on each wing of the Bridge. | SART can be taken off easily from the stow position on each wing on Bridge.
2. Operation panel | Switch works properly | Switch works properly
3. Function | When power is on, a light-emitting diode lights and SART trace can be viewed on X-band radar. | When power is on, a light-emitting diode lights and SART works on X-band.
| （emitting time shall be as short as possible.) | （emitting time shall be as short as possible.)
4. Expiration date label | Expiration date of battery described on the label. | Expiration date described on the label
5. Test report etc. | The test report is on board the ship. | The test report is on board the ship.
Type： | Serial No.:
Installation and function Check/Test
Check Item | Confirmation |  | Result
1. Installation | SART can be taken off easily from the stow position on each wing on Bridge. | SART can be taken off easily from the stow position on each wing on Bridge.
2. Operation panel | Switch works properly | Switch works properly
3. Function | When power is on, a light-emitting diode lights and SART trace can be viewed on X-band radar. | When power is on, a light-emitting diode lights and SART works on X-band.
| （emitting time shall be as short as possible.) | （emitting time shall be as short as possible.)
4. Expiration date label | Expiration date of battery described on the label. | Expiration date described on the label
5. Test report etc. | The test report is on board the ship. | The test report is on board the ship.
Type： | Serial No.:
Installation and function Check/Test
Check Item | Confirmation |  | Result
1. Installation | SART can be taken off easily from the stow position on each wing on Bridge. | SART can be taken off easily from the stow position on each wing on Bridge.
2. Operation panel | Switch works properly | Switch works properly
3. Function | When power is on, a light-emitting diode lights and SART trace can be viewed on X-band radar. | When power is on, a light-emitting diode lights and SART works on X-band.
| （emitting time shall be as short as possible.) | （emitting time shall be as short as possible.)
4. Expiration date label | Expiration date of battery described on the label. | Expiration date described on the label
5. Test report etc. | The test report is on board the ship. | The test report is on board the ship.
Installation Company: |  | Vessel's Name:
Installed by: |  | Approved by:

## EPIRB
Equipment : EPIRB
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper.
Check Item | Confirmation | Result
1. Installation
When EPIRB is released, no obstructions are near the release area.
No damage to EPIRB itself and the case, and they are clean of any paint or stain etc.
Ftting bolts are fastened properly.
2. Operation panel | Switch works properly
3. Function
Test mode | Turn the mode switch to TEST and then the light-emitting diode is lit and the strobe light flashes.
4. Label | ID, expiration date of battery, expiration date of water pressure sensor, etc.
5. IＤ | ID, by using ID writer etc..
6. Test report | Contents to be written in are set correctly.
Installation Company: | Vessel's Name:
Installed by: | Approved by:

## Onboard Communication
Equipment : Onboard Communication System
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper.
Check Item | Confirmation | Result
1. Appearance check
1.1 Case / strap | No damage to the case and the strap, and they are clean.
1.2 Fitting of antenna | The antenna is fitted on the main unit without looseness.
2. Display
2.1 Display | When the unit is activated, LED lights.
2.2 Operation panel | All switches and volumes work properly.
3. Function
3.1 Receiving | Noise from speaker is heard.
3.2 Squelch | when the squelch is turned CCW, noise can be heard. When the squelch is turned CW, noise is wiped out.
3.3 Communication | Communicate with another transceiver equipment and confirm that communication can be achieved properly on both sides.
4. Battery charger | Charger charges the onboard communication equipment and the lamp on the charger lights.
5. Option | The tone squelch function regarding all tone.
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper.
Check Item | Confirmation | Result
1. Appearance check
1.1 Case / strap | No damage to the case and the strap, and they are clean.
1.2 Fitting of antenna | The antenna is fitted on the main unit without looseness.
2. Display
2.1 Display | When the unit is activated, LED lights.
2.2 Operation panel | All switches and volumes work properly.
3. Function
3.1 Receiving | Noise from speaker is heard.
3.2 Squelch | when the squelch is turned CCW, noise can be heard. When the squelch is turned CW, noise is wiped out.
3.3 Communication | Communicate with another transceiver equipment and confirm that communication can be achieved properly on both sides.
4. Battery charger | Charger charges the onboard communication equipment and the lamp on the charger lights.
5. Option | The tone squelch function regarding all tone.
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper.
Check Item | Confirmation | Result
1. Appearance check
1.1 Case / strap | No damage to the case and the strap, and they are clean.
1.2 Fitting of antenna | The antenna is fitted on the main unit without looseness.
2. Display
2.1 Display | When the unit is activated, LED lights.
2.2 Operation panel | All switches and volumes work properly.
3. Function
3.1 Receiving | Noise from speaker is heard.
3.2 Squelch | when the squelch is turned CCW, noise can be heard. When the squelch is turned CW, noise is wiped out.
3.3 Communication | Communicate with another transceiver equipment and confirm that communication can be achieved properly on both sides.
4. Battery charger | Charger charges the onboard communication equipment and the lamp on the charger lights.
5. Option | The tone squelch function regarding all tone.
Installation Company: | Vessel's Name:
Installed by: | Approved by:
Equipment : Onboard Communication System
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper.
Check Item | Confirmation | Result
1. Appearance check
1.1 Case / strap | No damage to the case and the strap, and they are clean.
1.2 Fitting of antenna | The antenna is fitted on the main unit without looseness.
2. Display
2.1 Display | When the unit is activated, LED lights.
2.2 Operation panel | All switches and volumes work properly.
3. Function
3.1 Receiving | Noise from speaker is heard.
3.2 Squelch | when the squelch is turned CCW, noise can be heard. When the squelch is turned CW, noise is wiped out.
3.3 Communication | Communicate with another transceiver equipment and confirm that communication can be achieved properly on both sides.
4. Battery charger | Charger charges the onboard communication equipment and the lamp on the charger lights.
5. Option | The tone squelch function regarding all tone.
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper.
Check Item | Confirmation | Result
1. Appearance check
1.1 Case / strap | No damage to the case and the strap, and they are clean.
1.2 Fitting of antenna | The antenna is fitted on the main unit without looseness.
2. Display
2.1 Display | When the unit is activated, LED lights.
2.2 Operation panel | All switches and volumes work properly.
3. Function
3.1 Receiving | Noise from speaker is heard.
3.2 Squelch | when the squelch is turned CCW, noise can be heard. When the squelch is turned CW, noise is wiped out.
3.3 Communication | Communicate with another transceiver equipment and confirm that communication can be achieved properly on both sides.
4. Battery charger | Charger charges the onboard communication equipment and the lamp on the charger lights.
5. Option | The tone squelch function regarding all tone.
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper.
Check Item | Confirmation | Result
1. Appearance check
1.1 Case / strap | No damage to the case and the strap, and they are clean.
1.2 Fitting of antenna | The antenna is fitted on the main unit without looseness.
2. Display
2.1 Display | When the unit is activated, LED lights.
2.2 Operation panel | All switches and volumes work properly.
3. Function
3.1 Receiving | Noise from speaker is heard.
3.2 Squelch | when the squelch is turned CCW, noise can be heard. When the squelch is turned CW, noise is wiped out.
3.3 Communication | Communicate with another transceiver equipment and confirm that communication can be achieved properly on both sides.
4. Battery charger | Charger charges the onboard communication equipment and the lamp on the charger lights.
5. Option | The tone squelch function regarding all tone.
Installation Company: | Vessel's Name:
Installed by: | Approved by:
Equipment : Onboard Communication System
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper.
Check Item | Confirmation | Result
1. Appearance check
1.1 Case / strap | No damage to the case and the strap, and they are clean.
1.2 Fitting of antenna | The antenna is fitted on the main unit without looseness.
2. Display
2.1 Display | When the unit is activated, LED lights.
2.2 Operation panel | All switches and volumes work properly.
3. Function
3.1 Receiving | Noise from speaker is heard.
3.2 Squelch | when the squelch is turned CCW, noise can be heard. When the squelch is turned CW, noise is wiped out.
3.3 Communication | Communicate with another transceiver equipment and confirm that communication can be achieved properly on both sides.
4. Battery charger | Charger charges the onboard communication equipment and the lamp on the charger lights.
5. Option | The tone squelch function regarding all tone.
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper.
Check Item | Confirmation | Result
1. Appearance check
1.1 Case / strap | No damage to the case and the strap, and they are clean.
1.2 Fitting of antenna | The antenna is fitted on the main unit without looseness.
2. Display
2.1 Display | When the unit is activated, LED lights.
2.2 Operation panel | All switches and volumes work properly.
3. Function
3.1 Receiving | Noise from speaker is heard.
3.2 Squelch | when the squelch is turned CCW, noise can be heard. When the squelch is turned CW, noise is wiped out.
3.3 Communication | Communicate with another transceiver equipment and confirm that communication can be achieved properly on both sides.
4. Battery charger | Charger charges the onboard communication equipment and the lamp on the charger lights.
5. Option | The tone squelch function regarding all tone.
Type： | Serial No.:
Installation and function Check/Test |  | Tick in the result column, if the result is proper.
Check Item | Confirmation | Result
1. Appearance check
1.1 Case / strap | No damage to the case and the strap, and they are clean.
1.2 Fitting of antenna | The antenna is fitted on the main unit without looseness.
2. Display
2.1 Display | When the unit is activated, LED lights.
2.2 Operation panel | All switches and volumes work properly.
3. Function
3.1 Receiving | Noise from speaker is heard.
3.2 Squelch | when the squelch is turned CCW, noise can be heard. When the squelch is turned CW, noise is wiped out.
3.3 Communication | Communicate with another transceiver equipment and confirm that communication can be achieved properly on both sides.
4. Battery charger | Charger charges the onboard communication equipment and the lamp on the charger lights.
5. Option | The tone squelch function regarding all tone.
Installation Company: | Vessel's Name:
Installed by: | Approved by:

## NAVTEX
Equipment : NAVTEX receiver
Type： | Serial No.:
Installation Check |  | Tick in the result column, if the result is proper.
Check Item | Confirmation | Result
1. Antenna
Antenna coupler | No damage to the whip antenna and/or no bend of the antenna.
The antenna is to be installed at the suitable position on the compass desk.
The coupler is fitted properly and the cables are fastened properly.
Earth wiring is proper.
2. Display
No damage to the display and it is clean of paint etc.
The main unit and printer(optional item) are installed properly.
Function Check
Check Item | Confirmation | Result
1. Checking operating state
1.1 Reception function (reception test) | Check that the NAVTEX message is received normally. Also, check from the past received messages that reception is normal.
1.2 Signal processor and controller | Check the station identification code and message type are printed on the first line of the message.
1.2.1 Report ID record
1.2.2 Message ID record | Check the message ID which is printed is also Stored MSG ID.
1.2.3 Report ID (message ID) setting | Check that the type of message to be received can be limited.
1.3 Self-diagnostic function | Confirm the self test function.
2. Switching to alternate power supply (only if power is fed) | Check that the receiver operates on DC power.
3. Printer function | Check that printout is normal.
3.1 Printer operation | Check that at least 32 characters are printed in a line.
3.2 Availability of consumables such as recording paper | If spare consumables are available, it is acceptable.
Installation Company: | Vessel's Name:
Installed by: | Approved by:

## Meteorologcal FAX
Equipment : Weather facsimile receiver
Type： | Serial No.:
Installation Check |  | Tick in the result column, if the result is proper.
Check Item | Confirmation | Result
1. Antenna
It is installed properly and is sufficiently seperated from the MF/HF Transmitter antenna.
2. Main unit
The fitting plate and the main unit are fitted properly.
Earth line is grounded properly as instructed.
Coaxial connector of the antenna is fitted to the antenna tightly.
Function Check
Check Item | Confirmation | Result
1. Checking display panel
1.1 Display panel state | Check that the indicator LED lights after power-on.
1.2 Operator panel state | Check that all keys and controls function normally.
2. Checking operation
2.1 Checking reception | Receive from fax broadcasting station to check that reception is normal.
2.2 Checking recording state | Receive from fax broadcasting station to check that reception is normal.
2.3 Checking program operation | Time is accurate?
Start the reception, recording and stop by setting the program. (auto mode)
3. Availability of consumables such as recording paper | If spare consumables are available, it is acceptable.
Installation Company: | Vessel's Name:
Installed by: | Approved by:

## INMARSAT FAX
Equipment : Inmarsat facsimile receiver
Type： | Serial No.:
Installation Check |  | Tick in the result column, if the result is proper.
Check Item | Confirmation | Result
1. Main unit
The fitting plate and the main unit are fitted properly.
Cable end is treated properly.
2. Up conversion transformer | For power transformer etc., conductors are connected without danger of electric shock.
Function Check
Check Item | Confirmation | Result
1. Checking display panel
1.1 Display panel state | Check that the indicator LED and LCD light after power-on.
1.2 Operator panel state | Check that all keys and controls function normally.
2. Checking operation
2.1 Checking copy | Check that data can be copied normally using the FAX test chart.
2.2 Checking communication | Perform communication test to check that transmission and reception are normal.
2.3 Checking self-test result | Perform self-test No.0 to No.3 to check that the result is normal.
3. Checking initial setting | Check that date and time, user name, and ship earth station number are correct.
4. Availability of consumables such as recording paper | If spare consumables are available, it is acceptable.
5. Checking protective gear | Protective cover of conductive part is in place.
Installation Company: | Vessel's Name:
Installed by: | Approved by:

## INMARSAT-F
Equipment : Inmarsat-F
Type： | Serial No.:
Installation Check | [6 empty] | Tick in the result column, if the result is proper.
Check Item | Confirmation | [5 empty] | Result
1. Antenna (ADE)
| The maintenance space is adequate. | The maintenance space is adequate. | The maintenance space is adequate. | The maintenance space is adequate. | The maintenance space is adequate. | The maintenance space is adequate.
Fitting bolts | Bolts for fitting antenna are fastened properly. | Bolts for fitting antenna are fastened properly. | Bolts for fitting antenna are fastened properly. | Bolts for fitting antenna are fastened properly. | Bolts for fitting antenna are fastened properly. | Bolts for fitting antenna are fastened properly.
Earth | Silicone rubber is applied on the bolts for fitting copper earth plate. | Silicone rubber is pasted on the bolts for fitting copper earth plate. | Silicone rubber is pasted on the bolts for fitting copper earth plate. | Silicone rubber is pasted on the bolts for fitting copper earth plate. | Silicone rubber is pasted on the bolts for fitting copper earth plate. | Silicone rubber is pasted on the bolts for fitting copper earth plate.
| The entrance cover of the antenna is fastened with bolts properly. | The entrance cover of the antenna is fastened with bolts properly. | The entrance cover of the antenna is fastened with bolts properly. | The entrance cover of the antenna is fastened with bolts properly. | The entrance cover of the antenna is fastened with bolts properly. | The entrance cover of the antenna is fastened with bolts properly.
Coaxial Cable | Connector for coaxial cable is connected and treated properly. | Connector for coaxial cable is connected and treated properly. | Connector for coaxial cable is connected and treated properly. | Connector for coaxial cable is connected and treated properly. | Connector for coaxial cable is connected and treated properly. | Connector for coaxial cable is connected and treated properly.
| Coaxial cable is fastened properly. | Coaxial cable is fastened properly. | Coaxial cable is fastened properly. | Coaxial cable is fastened properly. | Coaxial cable is fastened properly. | Coaxial cable is fastened properly.
2. Display unit (BDE)
| All bolts for fitting display unit are fastened properly. | All bolts for fitting display unit are fastened properly. | All bolts for fitting display unit are fastened properly. | All bolts for fitting display unit are fastened properly. | All bolts for fitting display unit are fastened properly. | All bolts for fitting display unit are fastened properly.
Telephone and optional equipment installed properly.
| Cables' end are treated properly. | Cables' end are treated properly. | Cables' end are treated properly. | Cables' end are treated properly. | Cables' end are treated properly. | Cables' end are treated properly.
Function Check
Check Item | Confirmation | [5 empty] | Result
1. Checking display panel
1.1 Display panel state
1.1.1 BDE | Check that the liquid crystal screen is displayed normally after power-on.
1.2 Operator panel state | Check that all keys function normally.
2.1 Checking antenna control
2.1.1 Checking attitude | Check that the gimbals axis is kept in a horizontal position 20 minutes after power-on.
2.1.2 Checking operation | Check that the antenna operates normally by inputting azimuth and elevation.
2.1.3 Checking following of gyro | Check that main ship gyro is followed normally
2.2 Checking reception | Check that the antenna is directed to the satellite, the device enters ready state, and the reception level becomes 57 or more 30 minutes after power-on.
2.3 Checking transmission | Perform communication test to check that transmission and reception are normal.
2.4 Checking communication
2.4.1 Telephone equipment operation | Check that voice call can be transmitted and received from all pieces of telephone equipment connected.
2.4.2 Facsimile operation | Check that facsimile data can be transmitted and received normally.
2.5 Checking alarm | Check that there is no alarm in the "alarm pack".
3. Rechecking initial setting | Recheck the ship earth station number, initial setting of telephone equipment, and date and time.
Check that ID is displayed beside the main unit.
4. Checking positional signal input | Position signal receiving form GPS.
5. Checking optional equipment operation | Optional equipment name ・ ＿＿＿＿＿＿＿ ・ ＿＿＿＿＿＿＿
・ ＿＿＿＿＿＿＿ ・ ＿＿＿＿＿＿＿
・ ＿＿＿＿＿＿＿ ・ ＿＿＿＿＿＿＿
Installation Company: | Vessel's Name:
Installed by: | Approved by:

## INMARSAT-B
Equipment : Inmarsat-B
Type： | Serial No.:
Installation Check | [6 empty] | Tick in the result column, if the result is proper.
Check Item | Confirmation | [5 empty] | Result
1. Antenna (ADE)
| The maintenance space is adequate. | The maintenance space is adequate. | The maintenance space is adequate. | The maintenance space is adequate. | The maintenance space is adequate. | The maintenance space is adequate.
Fitting bolts | Bolts for fitting the antenna are fastened properly. | Bolts for fitting the antenna are fastened properly. | Bolts for fitting the antenna are fastened properly. | Bolts for fitting the antenna are fastened properly. | Bolts for fitting the antenna are fastened properly. | Bolts for fitting the antenna are fastened properly.
Earth | Silicone rubber is applied on the bolts for fitting copper earth plate. | Silicone rubber is pasted on the bolts for fitting copper earth plate. | Silicone rubber is pasted on the bolts for fitting copper earth plate. | Silicone rubber is pasted on the bolts for fitting copper earth plate. | Silicone rubber is pasted on the bolts for fitting copper earth plate. | Silicone rubber is pasted on the bolts for fitting copper earth plate.
| The entrance cover of the antenna is fastened with bolts properly. | The entrance cover of the antenna is fastened with bolts properly. | The entrance cover of the antenna is fastened with bolts properly. | The entrance cover of the antenna is fastened with bolts properly. | The entrance cover of the antenna is fastened with bolts properly. | The entrance cover of the antenna is fastened with bolts properly.
Coaxial Cable | Connector for coaxial cable is connected and treated properly. | Connector for coaxial cable is connected and treated properly. | Connector for coaxial cable is connected and treated properly. | Connector for coaxial cable is connected and treated properly. | Connector for coaxial cable is connected and treated properly. | Connector for coaxial cable is connected and treated properly.
| Coaxial cable is fastened properly. | Coaxial cable is fastened properly. | Coaxial cable is fastened properly. | Coaxial cable is fastened properly. | Coaxial cable is fastened properly. | Coaxial cable is fastened properly.
2. Display unit (BDE)
| All bolts for fitting the display unit are fastened properly. | All bolts for fitting the display unit are fastened properly. | All bolts for fitting the display unit are fastened properly. | All bolts for fitting the display unit are fastened properly. | All bolts for fitting the display unit are fastened properly. | All bolts for fitting the display unit are fastened properly.
| Telephone and optional equipment such as PC etc. are installed properly. | Telephone and optional equipment such as PC etc. are installed properly. | Telephone and optional equipment such as PC etc. are installed properly. | Telephone and optional equipment such as PC etc. are installed properly. | Telephone and optional equipment such as PC etc. are installed properly. | Telephone and optional equipment such as PC etc. are installed properly.
| Cables' end are treated properly. | Cables' end are treated properly. | Cables' end are treated properly. | Cables' end are treated properly. | Cables' end are treated properly. | Cables' end are treated properly.
Function Check
Check Item | Confirmation | [5 empty] | Result
1. Checking display panel
1.1 Display panel state
1.1.1 BDE | Check that all green LEDs on power supply unit light three minutes after power-on.
1.1.2 VDU（Class1） | Check that there is no abnormality in display panel.
1.1.3 OPU（Class2） | Check that there is no abnormality in LED display panel.
1.2 Operator panel state | Check that all keys function normally.
2. Checking operating state
2.1 Checking antenna control
2.1.1 Checking attitude | Check that the gimbals axis is kept in a horizontal position 20 minutes after power-on.
2.1.2 Checking operation | Check that the antenna operates normally by inputting azimuth and elevation.
2.1.3 Checking following of gyro | Check that main ship gyro is followed normally
2.2 Checking reception | Check that the device enters ready state and the reception level becomes 60 or more when the antenna is directed to the satellite 30 minutes after power-on.
2.3 Checking transmission | Perform a transmission test with the antenna shifted 30 degrees or more from the satellite to check that EIRP is 31 to 34.
2.4 Printer function
2.4.1 Printer operation | Check that printout is normal.
Check that 40 characters or more are printed per line.
2.4.2 Availability of consumables such as recording paper | If there are spare consumables, it is acceptable.
2.5 Checking communication
2.5.1 Telephone equipment operation | Check that voice call can be transmitted and received from all pieces of telephone equipment connected.
2.5.2 Facsimile operation | Check that facsimile data can be transmitted and received normally.
2.5.3 Telex (Class 1)
2.5.3.1 Checking transmission and reception | Check that telex can be transmitted and received normally.
2.5.3.2 Checking answer back | Check that answer back is registered normally.
2.6 Checking self-test result | Perform self-test No.1 to No.5 to check that all results are normal.
2.7 Checking alarm | Print alarm back on the printer to check that no abnormal alarm occurs in the alarm back.
3. Rechecking initial setting | Recheck the ship earth station number, initial setting of telephone equipment, and date and time.
Check that ID is displayed beside the VDU.
4. Checking positional signal input | Positional signal supply source ( ) Type of positional signal ( )
5. Checking optional equipment operation | Optional equipment name ・ ＿＿＿＿＿＿＿ ・ ＿＿＿＿＿＿＿ |  | • ______________ • ______________
・ ＿＿＿＿＿＿＿ ・ ＿＿＿＿＿＿＿
・ ＿＿＿＿＿＿＿ ・ ＿＿＿＿＿＿＿
Installation Company: | Vessel's Name:
Installed by: | Approved by:

## INMARSAT-C
Equipment : Inmarsat-C
Type： | Serial No.:
Installation Check |  |  | Tick in the result column, if the result is proper.
Check Item | Confirmation |  | Result
1. EME unit
The maintenance space is adequate.
Fitting bolts | Stainless band for fititng the antenna is fastened properly.
Earth | Silicone rubber is pasted on the bolts for fitting copper earth plate.
Coaxial Cable | Connector for coaxial cable is connected and treated properly.
Coaxial cable is fastened properly.
２．IME etc. units
All bolts for fitting IME unit are fastened properly.
DTE and optional equipment such as PC etc. are installed properly.
Cables' end are treated properly.
Function Check
Check Item | Confirmation |  | Result
1. Checking display unit
1.1 Display unit state | Check that there is no abnormality in liquid crystal display panel.
Check that all IME indicators light at power-on.
1.2 Alarm device state | Check that the audible alarm sounds if an HIGH PRIORITY message is received, the printer runs out of paper, and ship position information is not updated four hours or more.
1.3 Operator panel state | Check that all keys function normally.
2. Checking operating state
2.1 Reception block function | Check that SYNC. LOG IN is on.
2.1.1 Tuning and synchronization display for carrier | Check that READY is displayed on liquid crystal display panel.
2.1.2 Reception test and checking reception record | Check that the EGC message is received normally. Also, check from the past received messages that reception is normal.
2.2 Printer function | Check that printout is normal.
2.2.1 Printer operation | Check that at least 40 characters are printed per line.
2.2.2 Availability of consumables such as recording paper | If spare consumables are available, it is acceptable.
2.3 Signal processor and controller function | Check from the EGC message printed out that RECEPTION TYPE is printed.
2.3.1 Report ID record
2.3.2 Message ID record | Message ID refers to the sequence No., but is not printed out.
Display the EGC message on the liquid crystal display panel to check message ID.
2.3.3 Report ID (message ID) setting | Check that RECEPTION TYPE can be selected.
3.1 Controller performance | Check that all functions in the main menu operate normally.
3.1.1 Display terminal operation
3.1.2 Message creation function | Check that a message can be created in EDIT mode.
3.2 Printer performance
3.2.1 Printer operation | Print the received message and transmitted message to check that the printer is normal.
3.2.2 Availability of consumables such as recording paper | If spare consumables are available, it is acceptable.
3.3 Transmission/reception block operation
3.3.1 Communication test | Perform communication test to check that the result is normal.
3.3.2 Reception level display | Check that the reception level is displayed on the top line of the screen.
3.3.3 Self-diagnostic function | PV test and alarm history function is used.
4. Switching to alternate power supply | Check that the device also operates on DC power.
5. Checking protective gear | Protective cover of conductive part is in place
6. Rechecking initial setting | Recheck MID and COMM DATE.
7. Checking positional signal input | Positional signal supply source ( ) Type of positional signal ( )
8. Checking optional equipment operation | Optional equipment name | • ______________ • ______________
• ______________ • ______________
Installation Company: | Vessel's Name:
Installed by: | Approved by:

## VHF
Equipment : VHF 1/2
No.1 Type： | Serial No.:
No.2 Type： | Serial No.:
Tick in the result column, if the result is proper.
Installation Check |  | VHF No.
Check Item | Confirmation | 1 | 2
1. Antenna
It is installed at the posiiton free from vibration and interferences.
It is installed properly as instructed.
2. Main unit installation
The main unit is installed properly.
Function Check |  | VHF No.
Check Item | Confirmation | 1 | 2
1. Checking display unit
1.1 Display unit state | Check whether all the characters, etc. are displayed on the LCD panel when turning on.
Check whether lightness of the display can be changed by the DIM switch.
1.2 Alarm device state | If two devices are installed, perform the test for both of the devices. When the DSC message (not distress message) is sent, check, in the other VHF radio equipment, that LED of the DSC display is lit, the message is displayed on the LCD panel and the speaker works.
1.3 Operator panel state | Check that the operator panel works normally by pressing the switches and turning the controls.
2.1 Controller performance | Check that controllers provide display according to its function and the function operates normally.
2.1.1 Operating state | Check that when the controller is shut down that only the power to that controller is turned off.
2.1.2 Radio wave issue display | Check that TX- is displayed on the liquid crystal display panel when the PTT button on the handset is pressed.
2.1.3 Channel 16 and channel 70 display and selection | Check that pressing CH16 and CH70 keys changes to respective channel for display.
2.1.4 Switching to other channel | If switching is normal, it is acceptable (within five seconds).
2.1.5 Transmission and reception switching | If switching is normal (instantaneous), it is acceptable (0.3 seconds).
2.1.6 Controller operation (priority from normal pilot position) | Check that the controller at the normal pilot position has priority.
2.2 Operating state of transmitter | Connect to dummy device and measure any frequency | deviation | deviation
2.2.1 Frequency deviation | (within 10 x 10-6). Measured frequency: kHz | Hz | Hz
2.2.2 Antenna power within +20, -50% | Use an inline VHF power meter to measure antenna power at any frequency. | output | output
| The power shall not exceed 25 W. Measured frequency: kHz | Ｗ | Ｗ
2.3 Checking operating state of receiver
2.3.1 Sensitivity | Check whether or not the sensitivity is good when the above test in 2.2.2 is performed.
2.3.2 Voice signal reception | Check whether or not the voice signal is received when the above test in 2.2.2 is performed.
2.3.3 Checking reception record | If the result of the above test in 2.3.2 is good, it is acceptable because the reception record cannot be checked.
2.4 Self-diagnostic function | Refer to instruction manual to perform self-test.
3. Checking DSC function
3.1 Distress alarm storage function | Create a distress message, turn off power once, and then turn it on again to check that the message is stored.
3.2 Distress message creation | Check that a distress message can be created.
3.3 Self-diagnostic function | Perform a self-test in DSC mode.
4. Switching to alternate power supply | Check that the device operates on DC power (DC is displayed on the liquid crystal display panel).
5. Checking protective gear | Protective cover of conductive part
6. Checking initial setting | Check self-ID and check that self-ID is displayed beside the controller.
7. Checking positional signal input | Positional signal supply source ( ) Type of positional signal ( )
8. Checking optional equipment operation | Optional equipment name • ______________ • ______________
• ______________ • ______________
Equipment : VHF guard receiver 2/2
Type： | Serial No.:
Check Item | Confirmation |  | Result
1. Checking display panel
1.1 Display panel state | Check that the LED lights and can be turned off by the dimmer after power-on.
1.2 Operator panel state | Check that all keys, switches, and controls function normally.
2. Checking operation
2.1 Checking reception | Check that reception tone is input.
2.2 Checking reception frequency change | Check that the reception frequency can be changed.
3. Checking protective gear | Protective cover of conductive part
Installation Company: | Vessel's Name:
Installed by: | Approved by:

## MF_HF1
Equipment : MF/HF Radio Equipment 1/2
No.1 Type： | Serial No.:
No.2 Type： | Serial No.: | [7 empty] | Tick in the result column, if the result is proper.
Installation Check | [8 empty] | Remorte Controller No.
Check Item | Confirmation |  |  |  |  | 1 | 2
1. Antenna
Standing antenna | Bolts for fitting base mast are fastened tightly. | Bolts for fitting base mast are fastened tightly. | Bolts for fitting base mast are fastened tightly. | Bolts for fitting base mast are fastened tightly. | Bolts for fitting base mast are fastened tightly.
| Whip antennas at the top are fitted tightly. | Whip antennas at the top are fitted tightly. | Whip antennas at the top are fitted tightly. | Whip antennas at the top are fitted tightly. | Whip antennas at the top are fitted tightly.
| Lead-in wire is fastened tightly and wire clipper is fastened tightly as well. | Lead-in wire is fastened tightly and wire clipper is fastened tightly as well. | Lead-in wire is fastened tightly and wire clipper is fastened tightly as well. | Lead-in wire is fastened tightly and wire clipper is fastened tightly as well. | Lead-in wire is fastened tightly and wire clipper is fastened tightly as well.
| No damage to the insulator, and it is clean of stain. | No damage to the insulator, and it is clean of stain. | No damage to the insulator, and it is clean of stain. | No damage to the insulator, and it is clean of stain. | No damage to the insulator, and it is clean of stain.
2. Antenna tuner
| All bolts for installation are fastened properly. | All bolts for installation are fastened properly. | All bolts for installation are fastened properly. | All bolts for installation are fastened properly. | All bolts for installation are fastened properly.
Earth | Earth plate is to be supplied by JRC, and welded to the ship's body. | Earth plate is to be supplied by JRC. | Earth plate is to be supplied by JRC. | Earth plate is to be supplied by JRC. | Earth plate is to be supplied by JRC.
| Copper earth plate of the main unit and earth plate are soldered together. | Copper earth plate of the main unit and earth plate are soldered up. | Copper earth plate of the main unit and earth plate are soldered up. | Copper earth plate of the main unit and earth plate are soldered up. | Copper earth plate of the main unit and earth plate are soldered up.
| The copper earth plate of the main unit is fitted at two points. | The copper earth plate of the main unit is fitted at two points. | The copper earth plate of the main unit is fitted at two points. | The copper earth plate of the main unit is fitted at two points. | The copper earth plate of the main unit is fitted at two points.
RBK line | RBK line is connected in the junction box. | RBK line is connected in the junction box. | RBK line is connected in the junction box. | RBK line is connected in the junction box. | RBK line is connected in the junction box.
| RBK line is cabled between the junction box and the tuner and it is connected to the terminals in the junction box and the tuner . | RBK line is cabled between the junction box and the tuner and it is connected to the terminals in the junction box and the tuner . | RBK line is cabled between the junction box and the tuner and it is connected to the terminals in the junction box and the tuner . | RBK line is cabled between the junction box and the tuner and it is connected to the terminals in the junction box and the tuner . | RBK line is cabled between the junction box and the tuner and it is connected to the terminals in the junction box and the tuner .
Coaxial cable and connectors. | Coaxial cable and connector soldered properly?
when installed on the weather deck | Cable glands are waterproofed. | Cables gland is waterproofed. | Cables gland is waterproofed. | Cables gland is waterproofed. | Cables gland is waterproofed.
| RF cables are waterproofed with tape. | RF cables are waterproofed with tape. | RF cables are waterproofed with tape. | RF cables are waterproofed with tape. | RF cables are waterproofed with tape.
| Lead-in wire is fastened. | Lead-in wire is fastened. | Lead-in wire is fastened. | Lead-in wire is fastened. | Lead-in wire is fastened.
| Loop of the lead-in wire is 100mm to 150mm in diameter. | Loop of the lead-in wire is 100mm to 150mm in diameter. | Loop of the lead-in wire is 100mm to 150mm in diameter. | Loop of the lead-in wire is 100mm to 150mm in diameter. | Loop of the lead-in wire is 100mm to 150mm in diameter.
Fasten cover of Junction box and Tuner.
3. Console | No looseness of fitting bolts. | No looseness of fitting bolts. | No looseness of fitting bolts. | No looseness of fitting bolts. | No looseness of fitting bolts.
Radio equipment, DTE, Keyboard, Printer | Fitted properly as instructed by the installation manual. | Fitted properly as instructed by the installation manual. | Fitted properly as instructed by the installation manual. | Fitted properly as instructed by the installation manual. | Fitted properly as instructed by the installation manual.
| No damage to the knobs and LCD etc. | No damage to the knobs and LCD etc. | No damage to the knobs and LCD etc. | No damage to the knobs and LCD etc. | No damage to the knobs and LCD etc.
Function Check | [8 empty] | Remorte Controller No.
Check Item | Confirmation |  |  |  |  | 1 | 2
1. Checking display unit
1.1 Display unit state | Check that there is no abnormality in liquid crystal display panel on MF/HF radio equipment. Also, check that the characters engraved and printed on pushbutton switches are normal.
2. Checking operating state
2.1 Controller performance
2.1.1 Operating state | Check that the display on the liquid crystal display panel changes according to the state when the dial is turned.
2.1.2 Radio wave issue display | Check that radio wave is displayed on the LCD panel of the MF/HF controller.
2.1.3 Switching to other channel | Check that the channel is switched.
2.2 Operating state of transmitter | Measured frequency (MF): |  | kHz |  | kHz | deviation MF |  | Hz | Hz
2.2.1 Frequency deviation (±10 Hz) | (HF) |  | kHz |  |  | deviation HF |  | Hz | Hz
2.2.2 Antenna power (＋20%,－50%) | Calculate antenna power by the expression I x E x efficiency to check that it is the specified power.
| Measured frequency (MF): |  | kHz Specified power (MF): |  | (W) | deviation MF |  | Hz | Hz
| (HF) |  | kHz | (HF) | (W) | deviation MF |  | Hz | Hz
2.2.3 Communication with party described on license | Perform communication in SSB mode to check that communication can be done normally.
2.3 Checking operating state of receiver | Set the reception frequency to the communication frequency to check whether or not the voice signal is received. Also, check the operation variable controls such as RF, AF, and BFO.
2.3.1 Voice signal reception
2.3.2 Checking reception record | Perform communication in SSB mode to check that communication can be done normally.
2.3.3 Sound from speaker, etc. | Check that sound is heard from the speaker of the MF/HF radio equipment and does not get distorted.
2.4 Self-diagnostic function | Perform self-test to check that the result is good.

## MF.HF２
Equipment : MF/HF Radio Equipment 2/2
Tick in the result column, if the result is proper.
Remorte Controller No.
Check Item | Confirmation |  |  | 1 | 2
3. Checking DSC function
3.1 Distress alarm storage function | Create a distress message, turn off power once, and then turn it on again to check that the message is stored.
3.2 Distress message creation | Check that a distress message can be created in a file.
3.3 Self-diagnostic function | Perform a self-test in DSC mode.
3.4 Display unit and alarm device state | Check that there is no abnormality in liquid crystal display panel on MF/HF radio equipment. Also, check that the characters engraved and printed on pushbutton switches are normal.
Check that the audible alarm sounds and the LED lights when the DSC signal is received or during a self-test.
3.5 Operator panel state | Check that display is changed and messages can be edited by pressing the menu button.
3.6 WKR distress frequency selection | Check that the LED at the frequency set in SETUP mode lights.
3.7 Reception function operation | Receive the DSC message from other station to check the operation of reception function.
3.8 Distress alarm storage function | If the distress alarm message can be received from other station, the distress alarm storage function can be checked. Up to 20 messages can be stored within 48 hours.
3.9 Acoustic property of speaker | Check the acoustic property when the above test in 3.7 is performed.
3.10 Reception test | Check reception when the above test in 3.7 is performed.
3.11 Checking reception record | Check the reception record when the above test in 3.7 is performed (attach the recording paper).
3.12 Test using self-diagnostic device | Perform the test if the above test in 3.7 cannot be performed.
4. Checking narrow-band direct printing telegraphic instrument function
4.1 Printer operation | Create a message in DTE to check printer operation.
4.2 Self-diagnostic function | Perform a self-test in DTE.
4.3 Communication test with coastal office | Select a proper coastal station and perform communication test (attach communication record).
4.4 Available of consumable such as recording paper | If spare consumables are available, it is acceptable.
5. Switching to alternate power supply | Check that the device operates and outputs data on DC power.
6. Checking protective gear | Protective cover of conductive part
7. Checking call sign and ID | Check call sign, DSC ID, NBDP ID, and AAB (check the position of DIP switch).
Check that the call sign and ID are displayed in or around the controller.
8. Legal document | Check whether legal documents are available.
9. Checking positional signal input | Positional signal supply source ( ) Type of positional signal ( )
10. Checking optional equipment operation Optional equipment name. | Optional equipment name | • ________________ • ________________
• ________________ • ________________
• ________________ • ________________
Installation Company: |  | Vessel's Name:
Installed by: |  | Approved by:

## BNWAS(1)
Equipment: BNWAS 1/2
Model: JCX-
Installation Check
Check Item | Confirmation | Result
1. Main Unit | Installation base is flat and even. (Uneven surfaces such as welding seems should be levelled )
Fixing bolts are tightened correctly.
Ground is connected.
Cables are fitted neatly and secured in place.
Nameplate sticker for display unit (JCX-***) is on the cover.
2. Display Unit (LED or LCD) | Fixing bolts are tightened correctly.
Cables are fitted neatly and secured in place.
Node ID and terminating resistance is configured correctly.
3. Reset Button | Fixing bolts are tightened correctly.
Cables are fitted neatly and secured in place.
4. Audible Alarm Buzzer | Fixing bolts are tightened correctly.
Cables are fitted neatly and secured in place.
5. Waterproof Reset Button | Fixing bolts are tightened correctly.
Cables are fitted neatly and secured in place.
6. Motion Sensor (option) | Fixing bolts are tightened correctly.
Fixing Bolt | Cables are fitted neatly and secured in place.
unit is kept out of direct sunlight or strong lights, and also kept away from rapid temperature change such as ventilation air flow.
7. LED Audible alarm Buzzer | Fixing bolts are tightened correctly.
(option) | Cables are fitted neatly and secured in place.
8. Contact Input 装置 | Fixing bolts are tightened correctly.
(option) | Cables are fitted neatly and secured in place.
9. Contact Output 装置 | Fixing bolts are tightened correctly.
(option) | Cables are fitted neatly and secured in place.
10. Ethernet Unit (option) | Fixing bolts are tightened correctly.
Cables are fitted neatly and secured in place.
11. Emergency Cal Button | Fixing bolts are tightened correctly.
(option) | Cables are fitted neatly and secured in place.
Remarks/Comments | The installation place of the audible alarm buzzer:
Function Check
Next Page

## BNWAS(2)
Equipment: BNWAS 2/2
Model: JCX-
Function Check
Check Item | Confirmation |  | Result
1. Main Controll Unit | Check and record the terminal voltage of AC power supply |  | Vac
| Check and record the terminal voltage of DC power supply |  | Vdc
Power on both AC and DC power supplies. Confirm the LED of SYSTEM ACTIVE on the display unit lights up and LED of SYSTEM FAIL is off and no error is occuring.
When the AC breaker is switched off, the LED of SYSTEM ACTIVE on the display unit blinks and 2nd remote audible alarm buzzer rings.
When the DC breaker is switched off, the LED of EMER SOURCE on the display unit blinks and 2nd remote audible alarm buzzer rings.
2. Function
2.1 Operation Mode | Set to AUTO MODE on the display unit. Confirm that timer starts to countdown when HCS signal is input from AUTO PILOT.
The timer starts to countdown when configuration is set to MANUAL ON on the display unit.
The timer does not start to countdown when configuration is set to MANUAL OFF on the display unit.
2.2 Reset Function | Reset button on the display unit works to reset timer.
Reset button and waterproof timer reset can reset the timer correctly.
2.3 Buzzer Text
2.4 Backup Officer
2.5 Alarm Stage
3. Alarm Outputs
Remarks/Comment
Installation Company: |  | Vessel's Name:
Installed by: |  | Approved by:

## VDR
Equipment: VDR/SVDR
MODEL: JCY-
Check Item | Confirmation | Result
1. Capsule | Fixing bolts are tightened correctly and sealed.
Cables are fitted neatly and secured in place.
Cable glands are fastened and waterproofed properly.
2. Connection Box | Installation base is flat and even. (Uneven surfaces such as welding seems should be leveled )
Fixing bolts are tightened correctly and sealed.
Cables are fitted neatly and secured in place.
Cables in the connection box is fixed appropriately.
3. Recording Controller | Installation base is flat and even. (Uneven surfaces such as welding seems should be leveled )
Fixing bolts are tightened correctly.
Ground is connected.
Cables are fitted neatly and secured in place.
4. Ditigal Signal Converter | Installation base is flat and even. (unit is not deformed or twisted due to uneven surface)
Fixing bolts are tightened correctly..
Ground is connected.
Cables are fitted neatly and secured in place.
5. Operation Panel | Fixing bolts are tightened correctly.
Cables are fitted neatly and secured in place.
6. Microphone Unit | Fixing bolts are tightened correctly.
Cables are fitted neatly and secured in place.
Remarks/Comments
Installation Company: | Vessel's Name:
Installed by: | Approved by: